## Sheet1
AllThatStuff

done
work in progress
need to do this

	want (1-5)	work (1-5)	NEXT STEPS	QUESTIONS
START MENU
select player piece	5
type in player names	3	2
game lobby / host or join games	2	4?
synchronize object ticker for all players	1	3
what happens if a player drops out?	4	2
start game / player who starts the game also starts with building & passes his selection of objects to other players	5	3
only start the game when at least 3 players joined	5	1	replace alert with pretty message
add music?	2	2

MAIN GAME
display joined players	5	1
drag&drop objects	5

players take turns	5	3
when builder is finished, send object position to other players	5	3
synchronize object positions in real-time	3	2	do it more elegantly?	right now I’m passing/updating all the objects on every mousemove.. is that bad?
“done” button and time limit for building	4	1
display card deck	5	3

make a guess & get points	5	3
display the answers & given points	5	2
end game & show winner	5	2
restart the game (same players / new players)	3	2
what happens if a player drops out during the game?	3	2
basic mobile support (drag&drop on touch)	4	3
mobile: different layout depending on current role	3	4

GENERAL
structure code / files				how to structure my code?
pre-load images	2	?		images and sounds have a loading time.. is there a way to pre-load all the images and sounds that will be used later?

STYLE & EXTRA FEATURES
show object descriptions on hover/some option	3	2
make objects turnable	4	2
animate points bubble up or down	3	3
sound/mute state icons	3	2
increase z-index also when object is clicked outside the construction area	2	1